## Instructions
KIPP Network Growth — Milestone & Dependency Planning
Prepared for the Network Growth Committee · To complete after the planning meeting
What we're asking you to do
Open the tab named for your department. It is PRE-FILLED with the current milestones from the Growth tool as a starting point. For each of the 8 schools opening in Fall 2027 and Fall 2028: review and correct the milestones, add any that are missing, and complete the blank columns — how long each milestone will take, the inputs you need from other teams (pick the department and describe exactly what you need), and the current status. Complete only your department's tab.
The 8 schools
Fall 2027 (opens Aug 2027 · FY28): Paterson ES2 · Paterson MS2 · Broward ES3 · Broward MS3
Fall 2028 (opens Aug 2028 · FY29): Broward ES4 · Broward MS4 · Newark ES6 · Newark MS6
Department tabs & owners
Real Estate | Owner: Doug Chu
Finance | Owner: Susie Chu
Regulatory | Owner: Gabriella DiFilippo
Talent | Owner: David Branson
Marketing & Recruitment | Owner: Maria-Cristina Ventresca
Advancement | Owner: Anne Tatreau
How to complete each row
1. Review each pre-filled milestone. Edit the wording, owner, or school if the current assumption is wrong. Delete any that don't apply.
2. Add new milestones on the blank rows below the pre-filled ones (the dropdowns already work there).
3. Estimate how long the milestone will take (a number) and pick the Unit (Days / Weeks / Months).
4. For each input you need from another team: pick the Department from the dropdown, then describe exactly what you need from them. Up to three per milestone; use Notes for more.
5. Set the Status: Not started, In progress, or Complete.
6. Target completion is pre-filled with the tool's current assumed date where one exists — correct it if needed.
Once every tab is complete, this workbook becomes the source for the project plan in the Growth tool (milestones → gates, each 'input needed' → a linked task from that team).

## Lists (hidden)
Schools | Status | Unit | Teams
Broward ES3 (Fall 2027) | Not started | Days | Real Estate
Broward MS3 (Fall 2027) | In progress | Weeks | Finance
Paterson ES2 (Fall 2027) | Complete | Months | Regulatory
Paterson MS2 (Fall 2027) |  |  | Talent
Broward ES4 (Fall 2028) |  |  | Marketing & Recruitment
Broward MS4 (Fall 2028) |  |  | Advancement
Newark ES6 (Fall 2028) |  |  | External / District
Newark MS6 (Fall 2028) |  |  | Other
Broward ES3 & MS3 (Fall 2027) |  |  | None
Paterson ES2 & MS2 (Fall 2027)
Broward ES4 & MS4 (Fall 2028)
Newark ES6 & MS6 (Fall 2028)
All Fall 2027 schools
All Fall 2028 schools
All 8 schools

## Real Estate
Real Estate — Growth Milestones & Dependencies
Tab owner: Doug Chu · Rows are pre-filled from the Growth tool — review & correct them, add missing milestones below, and complete the blank columns (duration, dependencies, status).
School(s) | Milestone owner | Big-picture milestone / objective | Status | Est. duration | Unit | Target completion | Dependency 1: Department | Dependency 1: What you need from them | Dependency 2: Department | Dependency 2: What you need from them | Dependency 3: Department | Dependency 3: What you need from them | Notes / sequencing
All 8 schools | Doug Chu | Assess market costs and develop project budgets | Not started |  |  | 2026-06-30
All 8 schools | Doug Chu | Develop market strategy for finding sites | Not started |  |  | 2026-06-30
Broward ES3 & MS3 (Fall 2027) | Doug Chu | Submit Building Notice for ES 3 and MS 3 | Not started |  |  | 2026-06-30
Broward ES4 & MS4 (Fall 2028) | Doug Chu | Submit Building Notice for ES 4 and MS 4 | Not started |  |  | 2026-06-30
Paterson ES2 & MS2 (Fall 2027) | Doug Chu | Sites identified for ES2 & MS2 | Not started |  |  | 2026-06-30
Broward ES3 & MS3 (Fall 2027) | Doug Chu | Site/Building Identified for ES3 & MS3 | Not started |  |  | 2027-06-30
Broward ES3 & MS3 (Fall 2027) | Doug Chu | Lease negotiated for ES3 & MS3 | Not started |  |  | 2027-06-30
Paterson ES2 & MS2 (Fall 2027) | Doug Chu | Lease(s) negotiated for ES2 & MS2 | Not started |  |  | 2027-06-30
Newark ES6 & MS6 (Fall 2028) | Doug Chu | Site identified for ES6 and MS6 | Not started |  |  | 2027-06-30
Broward ES4 & MS4 (Fall 2028) | Doug Chu | Site/Building Identified for ES4 & MS4 | Not started |  |  | 2028-06-30
Broward ES4 & MS4 (Fall 2028) | Doug Chu | Lease negotiated for ES4 & MS4 | Not started |  |  | 2028-06-30
Newark ES6 & MS6 (Fall 2028) | Doug Chu | Lease(s) Negotiated for ES6 and MS6 | Not started |  |  | 2028-06-30
All 8 schools | Doug Chu | Site/Building Identified for ES 6 | Not started
All 8 schools | Doug Chu | Site/Building Identified for MS 6 | Not started

## Finance
Finance — Growth Milestones & Dependencies
Tab owner: Susie Chu · Rows are pre-filled from the Growth tool — review & correct them, add missing milestones below, and complete the blank columns (duration, dependencies, status).
School(s) | Milestone owner | Big-picture milestone / objective | Status | Est. duration | Unit | Target completion | Dependency 1: Department | Dependency 1: What you need from them | Dependency 2: Department | Dependency 2: What you need from them | Dependency 3: Department | Dependency 3: What you need from them | Notes / sequencing
All 8 schools | Susie Chu | Updated 10-15 school financial model for South Florida | Not started |  |  | 2026-06-30
All 8 schools | Susie Chu | Updated 5-school financial model for Paterson | Not started |  |  | 2026-06-30
Paterson ES2 & MS2 (Fall 2027) | Susie Chu | Financing / affordability analysis done for ES2 and MS2 sites | Not started |  |  | 2026-06-30
All 8 schools | Susie Chu | Updated 14-school financial model for Newark | Not started |  |  | 2026-06-30
Broward ES3 & MS3 (Fall 2027) | Susie Chu | Financing / affordability analysis done for ES3 and MS3 sites | Not started |  |  | 2027-06-30
Broward ES3 & MS3 (Fall 2027) | Susie Chu | CSP Applications for ES3 and MS3 submitted | Not started |  |  | 2027-06-30
Paterson ES2 & MS2 (Fall 2027) | Susie Chu | CSP Applications for ES2 and MS2 submitted | Not started |  |  | 2027-06-30
Broward ES4 & MS4 (Fall 2028) | Susie Chu | Financing / affordability analysis done for ES4 and MS4 sites | Not started |  |  | 2028-06-30
Broward ES4 & MS4 (Fall 2028) | Susie Chu | CSP Applications for ES4 and MS4 submitted | Not started |  |  | 2028-06-30

## Regulatory
Regulatory — Growth Milestones & Dependencies
Tab owner: Gabriella DiFilippo · Rows are pre-filled from the Growth tool — review & correct them, add missing milestones below, and complete the blank columns (duration, dependencies, status).
School(s) | Milestone owner | Big-picture milestone / objective | Status | Est. duration | Unit | Target completion | Dependency 1: Department | Dependency 1: What you need from them | Dependency 2: Department | Dependency 2: What you need from them | Dependency 3: Department | Dependency 3: What you need from them | Notes / sequencing
All 8 schools | Gabriella DiFilippo | Receive buildling lease with minimum terms mentioned | Not started |  |  | 2026-03-31
All 8 schools | Gabriella DiFilippo | Final greenlighting decision ion whether to add 4-5 new schools in Broward/Miami | Not started |  |  | 2026-06-30
All 8 schools | Gabriella DiFilippo | Obtain charter amendment for TEAM to expand to East Ward | Not started |  |  | 2026-06-30
All 8 schools | Anne Tatreau | Recruit and select 2-3 new board members | Not started |  |  | 2026-06-30
All 8 schools | Gabriella DiFilippo | Broward NOI + PBA approved | Not started |  |  | 2026-09-30
Broward ES3 & MS3 (Fall 2027) | Gabriella DiFilippo | Transition ES3 & MS3 to Regional Operations (prep for FDOS) | Not started |  |  | 2026-12-31
Paterson ES2 & MS2 (Fall 2027) | Gabriella DiFilippo | Transition ES2 & MS2 to Regional Operations (prep for FDOS) | Not started |  |  | 2026-12-31
All 8 schools | Gabriella DiFilippo | Paterson expansion to 2,600 students apprroved during charter renewal | Not started |  |  | 2027-03-31
All 8 schools | Kyle Rosenkrans | Secure FY27 SOH grant | Not started |  |  | 2027-06-30
All 8 schools | Anne Tatreau | 1 new UHNW board member | Not started |  |  | 2027-06-30
All 8 schools | Gabriella DiFilippo | Final greenlighting decision on whether to grow to East Ward | Not started |  |  | 2027-06-30
All 8 schools | Anne Tatreau | 1 new UHNW Paterson board member | Not started |  |  | 2027-06-30
Broward ES4 & MS4 (Fall 2028) | Gabriella DiFilippo | Transition ES4 & MS4 to Regional Operations (prep for FDOS) | Not started |  |  | 2027-12-31
All 8 schools | Kyle Rosenkrans | Secure FY28 SOH grant | Not started |  |  | 2028-06-30
All 8 schools | Anne Tatreau | 1 new UHNW board member | Not started |  |  | 2028-06-30
Newark ES6 & MS6 (Fall 2028) | Gabriella DiFilippo | Transition ES6 & MS6 to Regional Operations (prep for FDOS) | Not started |  |  | 2028-06-30
All 8 schools | Kyle Rosenkrans | Secure FY29 SOH grant | Not started |  |  | 2029-06-30
All 8 schools | Anne Tatreau | 1 new UHNW board member | Not started |  |  | 2029-06-30
All 8 schools | Kyle Rosenkrans | Secure FY30 SOH grant | Not started |  |  | 2030-06-30

## Talent
Talent — Growth Milestones & Dependencies
Tab owner: David Branson · Rows are pre-filled from the Growth tool — review & correct them, add missing milestones below, and complete the blank columns (duration, dependencies, status).
School(s) | Milestone owner | Big-picture milestone / objective | Status | Est. duration | Unit | Target completion | Dependency 1: Department | Dependency 1: What you need from them | Dependency 2: Department | Dependency 2: What you need from them | Dependency 3: Department | Dependency 3: What you need from them | Notes / sequencing
Broward ES3 & MS3 (Fall 2027) | David Branson | School leaders and DSOs for ES3 and MS3 are hired into a fellowship program. | Not started |  |  | 2026-06-30
All 8 schools | David Branson | Additional regional leadership roles hired | Not started |  |  | 2026-06-30
Paterson ES2 & MS2 (Fall 2027) | David Branson | School leaders and DSOs for ES2 and MS2 are hired into a fellowship program. | Not started |  |  | 2026-06-30
All 8 schools | David Branson | Additional regional leadership roles hired | Not started |  |  | 2026-06-30
Broward ES3 & MS3 (Fall 2027) | David Branson | Staff & Teachers for ES3 and MS3 are hired | Not started |  |  | 2027-06-30
Broward ES4 & MS4 (Fall 2028) | David Branson | School leaders and DSOs for ES4 and MS4 are hired into a fellowship program. | Not started |  |  | 2027-06-30
All 8 schools | David Branson | Additional regional leadership roles hired | Not started |  |  | 2027-06-30
Paterson ES2 & MS2 (Fall 2027) | David Branson | Staff & Teachers for ES2 and MS2 are hired | Not started |  |  | 2027-06-30
All 8 schools | David Branson | Additional regional leadership roles hired | Not started |  |  | 2027-06-30
Broward ES4 & MS4 (Fall 2028) | David Branson | Staff & Teachers for ES4 and MS4 are hired | Not started |  |  | 2028-06-30
All 8 schools | David Branson | Additional regional leadership roles hired | Not started |  |  | 2028-06-30

## Marketing & Recruitment
Marketing & Recruitment — Growth Milestones & Dependencies
Tab owner: Maria-Cristina Ventresca · Rows are pre-filled from the Growth tool — review & correct them, add missing milestones below, and complete the blank columns (duration, dependencies, status).
School(s) | Milestone owner | Big-picture milestone / objective | Status | Est. duration | Unit | Target completion | Dependency 1: Department | Dependency 1: What you need from them | Dependency 2: Department | Dependency 2: What you need from them | Dependency 3: Department | Dependency 3: What you need from them | Notes / sequencing
All 8 schools | Maria-Cristina Ventresca | Build New Region Launch Playbook & "starter kit" | Not started |  |  | 2026-12-31
Broward ES3 (Fall 2027) | Maria-Cristina Ventresca | Enrollment ramp to target applications for ES3 | Not started |  |  | 2027-12-31
Broward MS3 (Fall 2027) | Maria-Cristina Ventresca | Enrollment ramp to target applications for MS3 | Not started |  |  | 2027-12-31
Paterson ES2 (Fall 2027) | Maria-Cristina Ventresca | Enrollment ramp to target applications for ES2 | Not started |  |  | 2027-12-31
Paterson MS2 (Fall 2027) | Maria-Cristina Ventresca | Enrollment ramp to target applications for MS2 | Not started |  |  | 2027-12-31
Broward ES3 (Fall 2027) | Maria-Cristina Ventresca | Finalize enrollment & lottery for ES3 | Not started |  |  | 2028-03-31
Broward MS3 (Fall 2027) | Maria-Cristina Ventresca | Finalize enrollment & lottery for MS3 | Not started |  |  | 2028-03-31
Paterson ES2 (Fall 2027) | Maria-Cristina Ventresca | Finalize enrollment & lottery for ES2 | Not started |  |  | 2028-03-31
Paterson MS2 (Fall 2027) | Maria-Cristina Ventresca | Finalize enrollment & lottery for MS2 | Not started |  |  | 2028-03-31
Broward ES4 (Fall 2028) | Maria-Cristina Ventresca | Enrollment ramp to target applications for ES4 | Not started |  |  | 2028-12-31
Broward MS4 (Fall 2028) | Maria-Cristina Ventresca | Enrollment ramp to target applications for MS4 | Not started |  |  | 2028-12-31
Newark ES6 (Fall 2028) | Maria-Cristina Ventresca | Enrollment ramp to target applications for ES6 | Not started |  |  | 2028-12-31
Newark MS6 (Fall 2028) | Maria-Cristina Ventresca | Enrollment ramp to target applications for MS6 | Not started |  |  | 2028-12-31
Broward ES4 (Fall 2028) | Maria-Cristina Ventresca | Finalize enrollment & lottery for ES4 | Not started |  |  | 2029-03-31
Broward MS4 (Fall 2028) | Maria-Cristina Ventresca | Finalize enrollment & lottery for MS4 | Not started |  |  | 2029-03-31
Newark ES6 (Fall 2028) | Maria-Cristina Ventresca | Finalize enrollment & lottery for ES6 | Not started |  |  | 2029-03-31
Newark MS6 (Fall 2028) | Maria-Cristina Ventresca | Finalize enrollment & lottery for MS6 | Not started |  |  | 2029-03-31

## Advancement
Advancement — Growth Milestones & Dependencies
Tab owner: Anne Tatreau · Rows are pre-filled from the Growth tool — review & correct them, add missing milestones below, and complete the blank columns (duration, dependencies, status).
School(s) | Milestone owner | Big-picture milestone / objective | Status | Est. duration | Unit | Target completion | Dependency 1: Department | Dependency 1: What you need from them | Dependency 2: Department | Dependency 2: What you need from them | Dependency 3: Department | Dependency 3: What you need from them | Notes / sequencing
All 8 schools | Anne Tatreau | Secure $7M South Florida growth capital | In progress |  |  | 2028-06-30
All 8 schools | Anne Tatreau | Secure $1.5M Paterson growth capital | In progress |  |  | 2028-06-30